## Blad1
Planning |  |  | Jaartal : 2013 - 2014
Onderdeel: |  |  | Week nr:
|  |  | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3
Aftrap |  |  | Week nr: 52: Kerstvakantie
Centrale bijeenkomst met Atos (Di) | bar: Week nr: 47
Centrale bijeenkomst (Di) | bar: Week nr: 48
Centrale bijeenkomst (Di) | bar: Week nr: 49
TestSessie1 a.d.h.v. testverslag (Wo) | bar: Week nr: 49
Centrale bijeenkomst (Di) | bar: Week nr: 50
Individuele assessments (Wo) | [12 empty] | Inleveren kleur anders? | bar: Week nr: 50
Centrale bijeenkomst (Di) | bar: Week nr: 51
TestSessie2 a.d.h.v. testverslag (Wo) | bar: Week nr: 51
Inleveren rapport (Do) | bar: Week nr: 2
Inleveren code (Do) | bar: Week nr: 3
Presentatie / demonstratie (Do) | bar: Week nr: 3
Controller | bar: Week nr: 47 to Week nr: 51; Week nr: 2 to Week nr: 3
Simulator | [12 empty] | Projectplan | >> opdrachtbeschrijving, globale (ruwe) taakverdeling en planning en mijlpalen, testplan, Eisen / wensen overzicht (tabel 'versimpelen'?) | bar: Week nr: 47 to Week nr: 51; Week nr: 2 to Week nr: 3
Management Interface (Android) | bar: Week nr: 49 to Week nr: 51; Week nr: 2 to Week nr: 3
1x per week vergaderen met 'begeleider'
vrij vergaderen met opdrachtgever
Documentatie | bar: Week nr: 46 to Week nr: 51; Week nr: 2
Analyse 1 (Do) | bar: Week nr: 46 to Week nr: 47
Tech doc 1 (Do) | bar: Week nr: 46 to Week nr: 47
Projectplan (Do) | bar: Week nr: 46 to Week nr: 47
Eindrapport | [12 empty] | << zie verslag_onderdelen.doc | bar: Week nr: 46 to Week nr: 51; Week nr: 2
|  | Ermee bezig | Week nr: 47: Uitloop; Week nr: 50: Perfectioneren
Wat wordt er bedoeld met 'Help-functie(p 6)'
Taakverdeling
| Wat |  | Week nr: 50: Wie
| Aftrap |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme