## Blad1
Planning |  | Jaartal : 2013 - 2014
Onderdeel: |  | Weeknummer:
|  | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3
Aftrap |  | Weeknummer: 52: Kerstvakantie
Centrale bijeenkomst met Atos (Di) | bar: Weeknummer: 47
Centrale bijeenkomst (Di) | bar: Weeknummer: 48
Centrale bijeenkomst (Di) | bar: Weeknummer: 49
TestSessie1 a.d.h.v. testverslag (Wo) | bar: Weeknummer: 48 to Weeknummer: 49
Centrale bijeenkomst (Di) | bar: Weeknummer: 50
Individuele assessments (Wo) | bar: Weeknummer: 50
Centrale bijeenkomst (Di) | bar: Weeknummer: 51
TestSessie2 a.d.h.v. testverslag (Wo) | bar: Weeknummer: 50 to Weeknummer: 51
Inleveren code (Do) | bar: Weeknummer: 47 to Weeknummer: 51; Weeknummer: 2 to Weeknummer: 3
Presentatie / demonstratie (Do) | bar: Weeknummer: 2 to Weeknummer: 3
Wiskunde | bar: Weeknummer: 47 to Weeknummer: 51; Weeknummer: 2
Junit | bar: Weeknummer: 48 to Weeknummer: 51; Weeknummer: 2
Controller (Server) | bar: Weeknummer: 47 to Weeknummer: 51; Weeknummer: 2 to Weeknummer: 3
networkConnection | bar: Weeknummer: 47 to Weeknummer: 49
xmlParser | bar: Weeknummer: 47 to Weeknummer: 49
jFrame | bar: Weeknummer: 47 to Weeknummer: 49
uploadFTP / JSONfile / Statistics | bar: Weeknummer: 48 to Weeknummer: 50
helpFunction | bar: Weeknummer: 50 to Weeknummer: 51; Weeknummer: 2
Protocol (Server/Client) | bar: Weeknummer: 47 to Weeknummer: 51; Weeknummer: 2 to Weeknummer: 3
networkConnection | bar: Weeknummer: 47 to Weeknummer: 49
Onderdelen (Kranen, boten etc.) | bar: Weeknummer: 47 to Weeknummer: 50
Simulator (Client) | bar: Weeknummer: 47 to Weeknummer: 51; Weeknummer: 2 to Weeknummer: 3
networkConnection | bar: Weeknummer: 47 to Weeknummer: 49
Modellen / Animaties | bar: Weeknummer: 47 to Weeknummer: 51
FlyByCamera | bar: Weeknummer: 47 to Weeknummer: 49
AGV's | bar: Weeknummer: 48 to Weeknummer: 51; Weeknummer: 2
Scene | bar: Weeknummer: 47 to Weeknummer: 49
Snelheidsoptimalisatie | bar: Weeknummer: 47 to Weeknummer: 51; Weeknummer: 2 to Weeknummer: 3
Management Interface (Mobiel) | bar: Weeknummer: 47 to Weeknummer: 51; Weeknummer: 2 to Weeknummer: 3
index (+ columnChart) | bar: Weeknummer: 48 to Weeknummer: 50
getData | bar: Weeknummer: 48 to Weeknummer: 50
getTime | bar: Weeknummer: 48 to Weeknummer: 50
Documentatie
Analyse 1 (Do) | bar: Weeknummer: 46 to Weeknummer: 47
Tech doc 1 (Do) | bar: Weeknummer: 46 to Weeknummer: 47
Projectplan 1 (Do) | [11 empty] | >> Opdrachtbeschrijving, globale (ruwe) taakverdeling en planning en mijlpalen, Eisen / wensen overzicht (tabel 'versimpelen'?) | bar: Weeknummer: 46 to Weeknummer: 47
Testplan 1 (Do) | bar: Weeknummer: 47 to Weeknummer: 48
Testverslag 1 (Di) | bar: Weeknummer: 48 to Weeknummer: 49
Tech doc 2 (Do) | bar: Weeknummer: 48 to Weeknummer: 49
Testplan 2 (Do) | bar: Weeknummer: 49 to Weeknummer: 50
Testverslag 2 (Di) | bar: Weeknummer: 50 to Weeknummer: 51
Tech doc 3 (Do) | bar: Weeknummer: 50 to Weeknummer: 51
Logboeken | [11 empty] | << Algemeen, niet gespecificeerd per persoon | bar: Weeknummer: 46 to Weeknummer: 51; Weeknummer: 2
Eindrapport (Do) | [11 empty] | << Zie verslag_onderdelen.doc | bar: Weeknummer: 46 to Weeknummer: 51; Weeknummer: 2
| Ermee bezig | Weeknummer: 46: Uitloop; Weeknummer: 49: Perfectioneren; Weeknummer: 52: Inleveren / vindt plaats
Taakverdeling
Onderdeel: |  | Weeknummer: 50: Wie:
Aftrap |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Centrale bijeenkomst met Atos (Di) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Centrale bijeenkomst (Di) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Centrale bijeenkomst (Di) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
TestSessie1 a.d.h.v. testverslag (Wo) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Centrale bijeenkomst (Di) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Individuele assessments (Wo) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Centrale bijeenkomst (Di) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
TestSessie2 a.d.h.v. testverslag (Wo) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Inleveren code (Do) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Presentatie / demonstratie (Do) |  | Weeknummer: 50: Melinda en Arjen (Joshua, Remco, Jeffrey en Yme)
Wiskunde |  | Weeknummer: 50: Melinda
JUnit |  | Weeknummer: 50: Joshua
Controller (Server) |  | Weeknummer: 50: Joshua, Remco en Yme
networkConnection |  | Weeknummer: 50: Remco
xmlParser |  | Weeknummer: 50: Remco
jFrame |  | Weeknummer: 50: Joshua
uploadFTP / JSONfile / Statistics |  | Weeknummer: 50: Remco
helpFunction |  | Weeknummer: 50: Joshua
Protcol (Server/Client) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
networkConnection |  | Weeknummer: 50: Remco (Yme)
Onderdelen (Kranen, boten etc.) |  | Weeknummer: 50: Joshua
Simulator (Client) |  | Weeknummer: 50: Melinda, Arjen en Jeffrey
networkConnection |  | Weeknummer: 50: Remco (Yme)
Modellen / Animaties |  | Weeknummer: 50: Melinda
FlyByCamera |  | Weeknummer: 50: Jeffrey
AGV's |  | Weeknummer: 50: Jeffrey
Scene |  | Weeknummer: 50: Arjen
Snelheidsoptimalisatie |  | Weeknummer: 50: Arjen
Management Interface (Mobiel) |  | Weeknummer: 50: Yme
index (+ columnChart) |  | Weeknummer: 50: Yme
getData |  | Weeknummer: 50: Yme
getTime |  | Weeknummer: 50: Yme
Documentatie
Analyse 1 (Do) |  | Weeknummer: 50: Joshua, Melinda, Arjen en Jeffrey (Remco en Yme)
Tech doc 1 (Do) |  | Weeknummer: 50: Remco, Melinda en Yme (Joshua, Arjen en Jeffrey)
Projectplan 1 (Do) |  | Weeknummer: 50: Melinda en Yme
Testplan 1 (Do) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Testverslag 1 (Di) |  | Weeknummer: 50: Joshua, Remco, Melinda en Yme
Tech doc 2 (Do) |  | Weeknummer: 50: Remco, Melinda en Yme (Joshua, Arjen en Jeffrey)
Testplan 2 (Do) |  | Weeknummer: 50: Joshua, Arjen en Yme
Testverslag 2 (Di) |  | Weeknummer: 50: Joshua en Yme
Tech doc 3 (Do) |  | Weeknummer: 50: Joshua en Yme
Logboeken |  | Weeknummer: 50: Arjen
Eindrapport (Do) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Rolverdeling
Projectleider |  | Weeknummer: 50: Melinda
Voorzitter |  | Weeknummer: 50: Melinda
Documentalist |  | Weeknummer: 50: Yme
Notulist |  | Weeknummer: 50: Yme