## Blad1
Planning |  | Jaartal : 2013 - 2014
Onderdeel: |  | Weeknummer:
|  | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3
Aftrap |  | Weeknummer: 52: Kerstvakantie
Centrale bijeenkomst met Atos (Di) | bar: Weeknummer: 47
Centrale bijeenkomst (Di) | bar: Weeknummer: 48
Centrale bijeenkomst (Di) | bar: Weeknummer: 49
TestSessie1 a.d.h.v. testverslag (Wo) | bar: Weeknummer: 48 to Weeknummer: 49
Centrale bijeenkomst (Di) | bar: Weeknummer: 50
Individuele assessments (Wo) | bar: Weeknummer: 50
Centrale bijeenkomst (Di) | bar: Weeknummer: 51
TestSessie2 a.d.h.v. testverslag (Wo) | bar: Weeknummer: 50 to Weeknummer: 51
Inleveren code (Do) | bar: Weeknummer: 46 to Weeknummer: 51; Weeknummer: 2 to Weeknummer: 3
Presentatie / demonstratie (Do) | bar: Weeknummer: 2 to Weeknummer: 3
Controller (Server) | bar: Weeknummer: 47 to Weeknummer: 51; Weeknummer: 2 to Weeknummer: 3
networkConnection | bar: Weeknummer: 47 to Weeknummer: 49
xmlParser | bar: Weeknummer: 47 to Weeknummer: 49
helpFunction | bar: Weeknummer: 50 to Weeknummer: 51; Weeknummer: 2
Simulator (Client) | bar: Weeknummer: 47 to Weeknummer: 51; Weeknummer: 2 to Weeknummer: 3
networkConnection | bar: Weeknummer: 47 to Weeknummer: 49
Management Interface (Android) | bar: Weeknummer: 48 to Weeknummer: 51; Weeknummer: 2 to Weeknummer: 3
Documentatie
Analyse 1 (Do) | bar: Weeknummer: 46 to Weeknummer: 47
Tech doc 1 (Do) | bar: Weeknummer: 46 to Weeknummer: 47
Projectplan v1 (Do) | [11 empty] | >> Opdrachtbeschrijving, globale (ruwe) taakverdeling en planning en mijlpalen, Eisen / wensen overzicht (tabel 'versimpelen'?) | bar: Weeknummer: 46 to Weeknummer: 47
Projectplan v2 (Vr) | [11 empty] | >> + Testplan | bar: Weeknummer: 46 to Weeknummer: 48
Logboeken | [11 empty] | << Algemeen, niet gespecificeerd per persoon | bar: Weeknummer: 46 to Weeknummer: 51; Weeknummer: 2
Eindrapport (Do) | [11 empty] | << Zie verslag_onderdelen.doc | bar: Weeknummer: 46 to Weeknummer: 51; Weeknummer: 2
| Ermee bezig | Weeknummer: 46: Uitloop; Weeknummer: 49: Perfectioneren; Weeknummer: 52: Inleveren / vindt plaats
Taakverdeling
Onderdeel: |  | Weeknummer: 50: Wie:
Aftrap |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Centrale bijeenkomst met Atos (Di) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Centrale bijeenkomst (Di) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Centrale bijeenkomst (Di) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
TestSessie1 a.d.h.v. testverslag (Wo) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Centrale bijeenkomst (Di) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Individuele assessments (Wo) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Centrale bijeenkomst (Di) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
TestSessie2 a.d.h.v. testverslag (Wo) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Inleveren code (Do) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Presentatie / demonstratie (Do) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Controller (Server) |  | Weeknummer: 50: Joshua, Remco en Yme
networkConnection |  | Weeknummer: 50: Remco en Yme
xmlParser |  | Weeknummer: 50: Remco
helpFunction
Simulator (Client) |  | Weeknummer: 50: Melinda, Arjen en Jeffrey
networkConnection |  | Weeknummer: 50: Remco en Yme
Management Interface (Android) |  | Weeknummer: 50: Yme, ???
Documentatie
Analyse 1 (Do) |  | Weeknummer: 50: Joshua, Melinda, Arjen en Jeffrey (Remco en Yme)
Tech doc 1 (Do) |  | Weeknummer: 50: Yme, ???
Projectplan v1 (Do) |  | Weeknummer: 50: Melinda en Yme
Projectplan v2 (Do) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Logboeken |  | Weeknummer: 50: Arjen
Eindrapport (Do) |  | Weeknummer: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Rolverdeling
Projectleider |  | Weeknummer: 50: Melinda
Voorzitter |  | Weeknummer: 50: Melinda
Documentalist |  | Weeknummer: 50: Yme
Notulist |  | Weeknummer: 50: Yme