## Blad1
Planning |  |  | Jaartal : 2013 - 2014
Onderdeel: |  |  | Week nr:
|  |  | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3
Aftrap |  |  | Week nr: 52: Kerstvakantie
Centrale bijeenkomst met Atos (Di) | bar: Week nr: 47
Centrale bijeenkomst (Di) | bar: Week nr: 48
Centrale bijeenkomst (Di) | bar: Week nr: 49
TestSessie1 a.d.h.v. testverslag (Wo) | bar: Week nr: 48 to Week nr: 49
Centrale bijeenkomst (Di) | bar: Week nr: 50
Individuele assessments (Wo) | bar: Week nr: 50
Centrale bijeenkomst (Di) | bar: Week nr: 51
TestSessie2 a.d.h.v. testverslag (Wo) | bar: Week nr: 50 to Week nr: 51
Inleveren code (Do) | bar: Week nr: 46 to Week nr: 51; Week nr: 2 to Week nr: 3
Presentatie / demonstratie (Do) | bar: Week nr: 2 to Week nr: 3
Controller (Server) | bar: Week nr: 47 to Week nr: 51; Week nr: 2 to Week nr: 3
Simulator (Client) | bar: Week nr: 47 to Week nr: 51; Week nr: 2 to Week nr: 3
Management Interface (Android) | bar: Week nr: 48 to Week nr: 51; Week nr: 2 to Week nr: 3
Documentatie
Analyse 1 (Do) | bar: Week nr: 46 to Week nr: 47
Tech doc 1 (Do) | bar: Week nr: 46 to Week nr: 47
Projectplan v1 (Do) | [12 empty] | >> Opdrachtbeschrijving, globale (ruwe) taakverdeling en planning en mijlpalen, testplan, Eisen / wensen overzicht (tabel 'versimpelen'?) | bar: Week nr: 46 to Week nr: 47
Projectplan v2 (Vr) | [12 empty] | >> + Testplan | bar: Week nr: 46 to Week nr: 48
Logboeken | [12 empty] | << Algemeen, niet gespecificeerd per persoon | bar: Week nr: 46 to Week nr: 51; Week nr: 2
Eindrapport (Do) | [12 empty] | << Zie verslag_onderdelen.doc | bar: Week nr: 46 to Week nr: 51; Week nr: 2
|  | Ermee bezig | Week nr: 46: Uitloop; Week nr: 49: Perfectioneren; Week nr: 52: Inleveren / vindt plaats
Taakverdeling
| Wat |  | Week nr: 50: Wie
| Aftrap |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
| Centrale bijeenkomst met Atos (Di) |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
| Centrale bijeenkomst (Di) |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
| Centrale bijeenkomst (Di) |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
| TestSessie1 a.d.h.v. testverslag (Wo) |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
| Centrale bijeenkomst (Di) |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
| Individuele assessments (Wo) |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
| Centrale bijeenkomst (Di) |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
| TestSessie2 a.d.h.v. testverslag (Wo) |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
| Inleveren code (Do) |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
| Presentatie / demonstratie (Do) |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
| Controller (Server) |  | Week nr: 50: Joshua, Remco en Yme
| Simulator (Client) |  | Week nr: 50: Melinda, Arjen en Jeffrey
| Management Interface (Android) |  | Week nr: 50: Yme, ???
Documentatie
| Analyse 1 (Do) |  | Week nr: 50: Joshua, Melinda, Arjen en Jeffrey (Remco en Yme)
| Tech doc 1 (Do) |  | Week nr: 50: Yme, ???
| Projectplan v1 (Do) |  | Week nr: 50: Melinda en Yme
| Projectplan v2 (Do) |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
| Logboeken |  | Week nr: 50: Arjen
| Eindrapport (Do) |  | Week nr: 50: Joshua, Remco, Melinda, Arjen, Jeffrey en Yme
Rolverdeling
| Projectleider |  | Week nr: 50: Melinda
| Voorzitter |  | Week nr: 50: Melinda
| Documentalist |  | Week nr: 50: Yme
| Notulist |  | Week nr: 50: Yme